## Data
Days in Build |  |  |  |  | Days in Accept |  |  |  | Days in Over Prod
B Busy | B Idle | B Blocked | B Wait for A | Total B | A Busy | A Idle | A Blocked | Total A | OP Busy | OP Idle | Total OP | Total | Date Planned | Date Started | Date Finished | Bug/Story | Stream | KB # | Description
3 | 0 | 0 | 2 | 5 | 5 | 4 | 0 | 9 | 0 | 0 | 0 | 14 | 2014-12-23 | 2015-01-23 | 2015-02-16 | Story | Infrastructure | 1580 | Switch to mail.fnb.co.za
11 | 0 | 0 | 0 | 11 | 4 | 0 | 0 | 4 | 0 | 1 | 1 | 16 | 2014-11-01 | 2015-12-03 | 2015-02-16 | Story | Infrastructure | 1577 | Pinecone restart SSIS package upon failure
2 | 1 | 14 | 0 | 17 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 19 | 2014-12-17 | 2014-12-17 | 2015-02-16 | Story | Infrastructure | 1564 | Pinecone defer start of package if another package in progress
5 | 3 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | ? | ? | ? | Story | Ashburton | ? | Bring ashburton SQL project into CI pipeline
19 | 1 | 0 | 0 | 20 | 5 | 0 | 0 | 5 | 0 | 1 | 1 | 26 | 2014-12-18 | 2014-12-18 | 2015-02-16 | Story | Infrastructure | 1565 | Provide message service for pinecone
7 | 0 | 15 | 0 | 22 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 26 | 2014-12-08 | 2014-12-08 | 2015-01-26 | Story | Infrastructure | 1557 | Publish nservicebus ssis completion status event
6 | 0 | 15 | 0 | 21 | 3 | 0 | 0 | 3 | 0 | 1 | 1 | 25 | 2014-02-08 | 2014-12-10 | 2015-01-26 | Story | Infrastructure | 1553 | Log nservicebus ssis package completion status
40 | 65 | 6 | 2 | 113 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 118 | 2014-09-15 | 2014-09-15 | 2015-02-19 | Story | PineCone | 1398 | Enable point in time portfolio structure for cube
4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 5 | 2014-11-14 | 2015-01-12 | 2015-01-26 | Bug | PineCone | 1549 | Correct duplicate entities for head-office-accounting
1 | 0 | 0 | 3 | 4 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 7 | 2015-01-29 | 2015-01-29 | 2015-02-17 | Story | Treasury | 1589 | Smart user access rights activity remove changed user status entries
1 | 0 | 0 | 0 | 1 | 4 | 4 | 0 | 8 | 0 | 0 | 0 | 9 | 2015-01-30 | 2015-01-30 | 2015-02-17 | Story | Treasury | 1588 | Stop logging empty parallel risk file imports as failures in riskey
1 | 0 | 0 | 4 | 5 | 3 | 1 | 1 | 5 | 0 | 8 | 8 | 18 | 2014-09-18 | 2014-09-18 | 2015-01-26 | Story | Treasury | 1493 | Create portfolio level smart user access report
23 | 0 | 0 | 2 | 25 | 8 | 9 | 0 | 17 | 0 | 1 | 1 | 43 | 2015-09-18 | 2014-09-18 | 2015-01-26 | Story | Treasury | 1493 | Refactor Smart Permission report
3 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 2 | 2 | 1 | 3 | 8 | 2014-10-29 | 2014-10-29 | 2014-12-02 | Story | Treasury | 1526 | Publish event when data files loaded and add ncd command handler to check for violations
9 | 3 | 0 | 0 | 12 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 15 | 2014-10-20 | 2014-10-20 | 2014-11-28 | Story | Treasury | 1508 | Ncd rates recon send e-mail when deals differ from quoted spread
2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 2 | 6 | 2014-12-03 | 2014-12-03 | 2014-12-09 | Bug | Treasury | 1545 | Fix activity same day report error from web menu
2 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2014-12-19 | 2014-12-19 | 2014-12-23 | Bug | Infrastructure | 1566 | SSIS package runner stays in pending state - add logging and throw error if in pending state for more than 1 minute
1 | 0 | 0 | 2 | 3 | 2 | 1 | 0 | 3 | 0 | 1 | 1 | 7 | 2014-11-19 | 2014-12-01 | 2014-12-09 | Story | Treasury | 1541 | Import riskwatch cashflows from previous instead of current folder
3 | 1 | 0 | 0 | 4 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 7 | 2014-12-02 | 2014-12-02 | 2014-12-09 | Story | Treasury | 1544 | Schedule ETL to run for month ends that fall on a weekend
11 | 42 | 4 | 0 | 57 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 59 | 2014-09-30 | 2014-10-09 | 2014-12-08 | Story | Ashburton | 1503 | Average balance sheet query change
2 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 2014-12-08 | 2014-12-08 | 2014-12-09 | Story | Infrastructure | 1554 | Create an event handler for hogan and quartz
7 | 3 | 0 | 2 | 12 | 3 | 0 | 0 | 3 | 1 | 2 | 3 | 18 | 2014-11-10 | 2014-11-10 | 2014-12-02 | Story | Treasury | 1530 | Smart user access rights activity report
13 | 6 | 0 | 0 | 19 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 20 | 2014-12-05 | 2014-12-05 | 2014-12-15 | Story | Infrastructure | 1562 | Make monitor an agent
18 | 4 | 0 | 4 | 26 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 31 | 2014-10-27 | 2014-10-28 | 2014-12-10 | Story | Infrastructure | 1524 | Pinecone create nservicebus saga to initiate ssis packages asynchronously from an event
8 | 0 | 0 | 0 | 8 | 3 | 0 | 0 | 3 | 0 | 2 | 2 | 13 | 2014-05-30 | 2015-01-07 | 2015-01-29 | Story | Treasury | 1425 | Support FXNDF instrument from Calypso
6 | 0 | 0 | 0 | 6 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 13 | 2014-11-19 | 2014-11-19 | 2015-01-27 | Story | Treasury | 1535 | Support calypso currency repo instrument
6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2015-01-14 | 2015-01-14 | ? | Story | PineCone | 1576 | Create SSIS Package to process the cube
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2014-12-04 | ? | ? | Story | PineCone | ? | Extend standard verification to include data flow expectations
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2014-12-04 | ? | ? | Story | PineCone | ? | Extend standard verification to include enabled/disabled
10 | 0 | 0 | 0 | 10 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 16 | 2014-10-30 | ? | ? | Bug | PineCone | 1550 | Correct behaviour of prerequisite testing for batches
7 | 0 | 0 | 2 | 9 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 15 | 2014-12-04 | ? | ? | Story | PineCone | 1551 | Handle non-windowed batches for targetd prerequisite batches
3 | 0 | 0 | 1 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 8 | 2014-12-17 | 2014-12-29 | 2015-01-06 | Story | Treasury | 1569 | Ncd intra-day allocation calculation adjustment
5 | 0 | 0 | 1 | 6 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 9 | 2014-11-27 | 2014-11-27 | 2014-12-09 | Story | Infrastructure | 1537 | Pinecone finish saga when ssis package triggered from nservicebus completed
1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2014-12-04 | 2014-12-04 | 2014-12-05 | Story | Infrastructure | 1552 | Migrate remaining loadexternalfiles based jobs to filedrop
2 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 2014-11-26 | 2014-11-26 | 2014-12-12 | Story | Infrastructure | 1539 | Bring filenotifier into CI process
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 4 | 5 | 7 | 2014-11-19 | 2014-11-19 | 2014-11-28 | Story | PineCone | 1534 | Add permission allocation to SSIS execution
6 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 12 | 2 | 2 | 4 | 22 | 2014-10-23 | 2014-10-24 | 2014-12-14 | Story | Infrastructure | 1525 | Migrate from imap to new drop folder in prod
8 | 0 | 0 | 0 | 8 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 11 | 2014-11-12 | 2014-11-12 | 2014-11-22 | Story | Infrastructure | 1532 | File notifier
1 | 0 | 0 | 2 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 2015-01-05 | 2015-01-06 | 2015-01-06 | Bug | Treasury | 1572 | Out of range exception for Getlastdayofpreviousmonth
1 | 0 | 0 | 5 | 6 | 3 | 1 | 0 | 4 | 0 | 1 | 1 | 11 | 2014-09-12 | 2014-09-12 | 2014-09-29 | Story | Ashburton | 1483 | Add asisa fees to maitland fees per class report
3 | 0 | 3 | 1 | 7 | 3 | 0 | 0 | 3 | 0 | 1 | 1 | 11 | 2014-09-18 | 2014-09-19 | 2014-10-06 | Story | Ashburton | 1494 | Update asisa report to conform to the now standard
1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | 0 | 2 | 2 | 6 | 2014-09-26 | 2014-09-26 | 2014-10-06 | Bug | Ashburton | 1496 | MV tottal and holding fields on asisa report are incorrect
1 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 2014-09-15 | 2014-09-23 | 2014-09-29 | Story | Treasury | 1495 | Load cfc balances to cubit
3 | 4 | 0 | 0 | 7 | 2 | 0 | 0 | 2 | 0 | 3 | 3 | 12 | 2014-09-15 | 2014-09-25 | 2014-09-29 | Story | Infrastructure | 1399 | Load external files should retry upon fail to import
2 | 6 | 2 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2014-09-11 | 2014-09-12 | no longer need | Story | Treasury | 1491 | Tds equivalent for valuation extended
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 4 | 2014-10-16 | 2014-10-17 | 2014-10-22 | Bug | Treasury | 1515 | Activity report error while trying to run the report on the web
9 | 0 | 0 | 0 | 9 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 11 | 2014-09-01 | 2014-10-20 | 2014-10-29 | Story | Treasury | 1523 | Create final swift billing report
3 | 0 | 1 | 0 | 4 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 6 | 2014-10-08 | 2014-10-23 | 2014-10-29 | Story | Treasury | 1521 | Support additional cash type receipts in motonovo process
2 | 0 | 0 | 1 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 6 | 2014-10-27 | 2014-10-27 | 2014-10-29 | Story | Treasury | 1522 | Clean up riskwatch ID on cashflow imports
3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 6 | 2014-09-11 | 2014-09-11 | 2014-09-12 | Story | Ashburton | 1480 | Add ashburton menu items
4 | 0 | 0 | 2 | 6 | 6 | 0 | 0 | 6 | 0 | 1 | 1 | 13 | 2014-09-15 | 2014-09-15 | 2014-09-29 | Story | Ashburton | 1481 | Split advent groupings to groupings and status
9 | 2 | 0 | 0 | 11 | 3 | 0 | 0 | 3 | 0 | 4 | 4 | 18 | 2014-09-15 | 2014-09-15 | 2014-09-29 | Story | Ashburton | 1470 | Load jersey fund holdings
6 | 3 | 9 | 0 | 18 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 19 | 2014-09-16 | 2014-09-16 | ? | Story | Ashburton | 1486 | New credit co report
6 | 0 | 0 | 0 | 6 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 7 | 2014-09-15 | 2014-09-15 | 2014-09-25 | Bug | Ashburton | 1457 | Correct trade link for cashflow funding
4 | 0 | 0 | 3 | 7 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 2014-09-15 | 2014-09-15 | 2014-09-25 | Story | PineCone | 1441 | Import smart hierarchies
1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2014-09-18 | 2014-09-18 | 2014-09-25 | Story | PineCone | ? | Import smart portfolio level access for audit
5 | 1 | 0 | 0 | 6 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 7 | 2014-10-23 | 2014-10-23 | 2014-10-30 | Story | Ashburton | 1520 | Ashburton ssis package runner
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 4 | 2014-10-16 | 2014-10-16 | 2014-10-22 | Story | Treasury | 1516 | Activity report for new deals should show period pnl same sign as period pnl/pv01
1 | 2 | 3 | 0 | 6 | 10 | 0 | 0 | 10 | 0 | 1 | 1 | 17 | 2014-09-16 | 2014-09-16 | 2014-10-06 | Story | Ashburton | 1485 | Update asisa report to conform to new standard no of accounts
2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 2014-10-16 | 2014-10-16 | 2014-10-22 | Story | Ashburton | 1517 | Create loader for maitland asisa report
2 | 4 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2014-10-08 | 2014-10-13 | 2014-10-22 | Story | Treasury | 1513 | Support additional ID pattern during riskwatch cashflow imports
6 | 0 | 1 | 2 | 9 | 4 | 0 | 0 | 4 | 0 | 1 | 1 | 14 | 2014-09-18 | 2014-09-18 | 2014-10-06 | Story | Ashburton | 1492 | Update asisa report weight avg duration
2 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 2014-10-03 | 2014-10-03 | 2014-10-06 | Story | Ashburton | 1510 | Import JSE dsv data for developer consumption
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2014-10-01 | 2014-10-02 | 2014-10-06 | Story | Treasury | 1507 | Make visible duplicate exchange rates in smart in exchange rates report
1 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 4 | 2014-09-30 | 2014-09-30 | 2014-10-06 | Story | Ashburton | 1501 | Create loader and repository for aci asset classes
1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 2014-10-20 | 2014-10-28 | 2014-10-29 | Story | Treasury | 1519 | Riskey data for london desks
5 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 8 | 2014-09-30 | 2014-09-30 | 2014-10-14 | Story | Infrastructure | 1500 | Setup KB DR machines
9 | 49 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 2014-09-15 | 2014-09-15 | no longer need | Story | Treasury | 1474 | Quick reports web ui
9 | 0 | 0 | 0 | 9 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 19 | 2014-10-03 | 2014-10-09 | 2014-10-22 | Story | Treasury | 1509 | Monitor ncd buy-backs as part of the ncd rates recon combo
10 | 3 | 0 | 0 | 13 | 2 | 0 | 0 | 2 | 0 | 3 | 3 | 18 | 2014-09-26 | 2014-09-26 | 2014-10-15 | Story | Infrastructure | 1512 | Move hogan cfc file handling to event based model as poc
1 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 5 | 5 | 8 | 2014-10-13 | 2014-10-13 | 2014-10-22 | Story | Ashburton | 1514 | Add additional columns to load silica holdings file command
21 | 1 | 0 | 0 | 22 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 23 | 2014-09-29 | 2014-09-30 | 2014-10-08 | Story | Ashburton | 1498 | Portfolio management flows report
7 | 0 | 0 | 1 | 8 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 12 | 2014-09-15 | 2014-09-15 | 2014-09-29 | Story | Ashburton | 1482 | Remove redundant IWebReport interface and amolgomate click and view report permission
3 | 0 | 0 | 0 | 3 | 3 | 0 |  | 3 | 0 | 0 | 0 | 6 | 2014-10-01 | 2014-10-01 | 2014-10-06 | Story | Ashburton | 1506 | Difference between silica and maitland

## Simplified Average Allocation
Bug/Story | Story
Stream | (Multiple Items)
Average Days in Build | Average Days in Accept | Average Days in Over Production
9.525 | 3.425 | 1

## Complete Average Allocation
Bug/Story | Story
Stream | (Multiple Items)
Build (Busy) | Build (Not Busy) | Buid (Blocked) | Build (Waiting for Accept) | Accept (Busy) | Accept (Not Busy) | Accept (Blocked) | Over Prod (Busy) | Over Production (Not Busy)
5.675 | 2.125 | 1.175 | 0.55 | 2.775 | 0.475 | 0.175 | 0.125 | 0.875

## Build Average Allocation
Bug/Story | Story
Stream | (Multiple Items)
Average of Bulid Busy | Average of Build Idle | Average of Build Blocked | Average of Build Wait for Accept
5.675 | 2.125 | 1.175 | 0.55

## Accept Average Allocation
Bug/Story | Story
Stream | (Multiple Items)
Average of Accept Busy | Average of Accept Idle | Average of Accept Blocked
2.775 | 0.475 | 0.175