## Data
Days in Build |  |  |  | Days in Accept |  |  | Days in Over Prod
B Busy | B Idle | B Wait for A | Total Build | A Busy | A Idle | Total Accept | OP Busy | OP Idle | Total OP | Total | Date Planned | Date Started | Date Finished | Work type | KB # | Description
3 | 0 | 0 | 3 | 4 | 0 | 4 | 0 | 0 | 0 | 7 | 2015-07-13 | 2016-01-18 | 2016-01-29 | Story | 1660 | Modify adjustments functionality to validate Trade ID
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2016-02-03 | 2016-02-05 | Story | 1754 | Modify NCD Potential Violation alert Ask label to Offer
3 | 0 | 0 | 3 | 5 | 1 | 6 | 0 | 0 | 0 | 9 | 2016-01-22 | 2016-01-22 | 2016-02-05 | Story | 1750 | Show current and previous adjustments in accountants combo
3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | 2016-02-18 | 2016-02-19 | Investigation |  | Monitor sensor osticket
8 | 7 | 0 | 15 | 2 | 1 | 3 | 0 | 0 | 0 | 18 |  | 2016-01-11 | 2016-03-11 | Story | 1751 | Make common into nuget pkg and consume from there
6 | 2 | 3 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 |  | 2016-02-10 | 2016-03-11 | Story |  | adTempus robocopy script instead of direct invocation
3 | 1 | 0 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 6 |  | 2016-02-25 | 2016-03-11 | Story | 1713 | Allow for the NCD potential violation alerts to be sent out only once
9 | 1 | 0 | 10 | 1 | 0 | 1 | 0 | 0 | 0 | 11 | 2015-10-09 | 2015-10-12 | 2016-03-11 | Story | 1708 | Flag trades as violation if traded rate was not the published rate within 5 min
2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2016-03-01 | 2016-03-11 | Investigation |  | HQLA breakdown email for Marta
3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2016-02-15 | 2016-02-15 | 2016-03-11 | Investigation |  | Quick report for FND average balances report
3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 4 |  | 2016-02-22 | 2016-03-11 | Investigation |  | Incorrect prime rate for nedbank in base rates report
2 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  | 2016-02-22 | 2016-03-11 | Investigation |  | Investigate FRN Trades import from Smart for tammy
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  | 2016-02-26 | 2016-03-11 | Investigation |  | Consolidate liquidity premium reports for 2015 for Shrinesan
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2016-02-22 | 2016-03-11 | Story |  | Support Turbo 6 for motonovo monthly runs
2 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 4 |  | 2016-01-29 | 2016-02-05 | Bug | 1753 | Trade level adjustments not working for non smart source system trades
2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2016-02-09 | 2016-02-09 | 2016-03-11 | Story | 1758 | Provide Rada recon reports for STF treasury department
2 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 4 | 2016-02-04 | 2016-02-04 | 2016-03-11 | Story | 1724 | Re-instate business unit column to daily deals extract data
3 | 0 | 0 | 3 | 6 | 2 | 8 | 4 | 0 | 4 | 15 |  | 2016-01-04 | 2016-03-11 | Story | 1743 | Feds summary dashboard: subtract clear funding values from pnl
2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 3 |  | 2016-02-16 | 2016-03-11 | Story |  | Motonovo turbo 6 takeon
2 | 1 | 0 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 5 |  | 2016-01-08 | 2016-03-11 | Story | 1746 | Automate thabo's valuation extended report for africa
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2016-02-04 | 2016-02-05 | Story | 1755 | Modified acc backdated report to be able to run it for a date range
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 2016-01-14 | 2016-01-18 | 2016-01-29 | Story | 1747 | Capture adjustments against accounts
2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 5 | 2016-01-14 | 2016-01-14 | 2016-01-29 | Story | 1748 | Portfolio level adjustments
1 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 3 |  | 2015-10-19 | 2015-10-23 | Story | 1222 | Remove TDS loader from ETL workflow and run it independently to improve efficiency
2 | 0 | 0 | 2 | 3 | 0 | 3 | 0 | 0 | 0 | 5 |  | 2015-10-23 | 2015-10-29 | Story | 1717 | Remove the send activity report to users command from ETL
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 |  | 2015-10-04 | 2015-10-04 | Investigation |  | Team city issue
1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2015-11-16 | 2016-01-21 | Investigation |  | TDS load is slow which causes us to fall behind quickly and catch up slowly
1 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 4 |  |  | 2016-01-21 | Story | 1728 | Display correct error when SSIS package fails in keyblade
3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 4 |  |  | 2016-01-21 | Investigation |  | Prevent file copy while in use for riskey files
2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | 2016-01-21 | Investigation |  | Rebuild trade position metrics index on pdv
8 | 6 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2015-11-30 | 2015-11-30 | 2016-01-21 | Story | 1730 | Delete unofficial datablocks from post dev
2 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2015-07-16 | 2015-07-16 | 2016-01-21 | Story | 1664 | Add investigate button on monitor
4 | 0 | 0 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 5 |  | 2016-01-05 | 2016-01-21 | Story | 1744 | Deploy settings separately from kb deploy
6 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 |  | 2016-01-06 | 2016-01-21 | Story | 1745 | Install OS ticket
5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2015-12-22 | 2015-12-22 | 2016-01-21 | Story |  | Team city 9
5 | 1 | 0 | 6 | 2 | 0 | 2 | 0 | 0 | 0 | 8 | 2015-10-26 |  | 2016-01-21 | Story | 1716 | Intraday liquidity risk management implement file format changes
11 | 3 | 1 | 15 | 4 | 0 | 4 | 0 | 0 | 0 | 19 |  | 2015-10-26 | 2015-11-10 | Story | 1718 | Remove K2 dependency from riskey
7 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2015-10-09 |  | 2016-01-21 | Story | 1709 | Create monitor sensor to ensure that we regularly receive ncd files from calypso
3 | 0 | 0 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 5 | 2015-11-26 |  | 2016-01-21 | Story | 1727 | Update chart of accounts number series for oracle balance sheet entries
8 | 7 | 0 | 15 | 4 | 1 | 5 | 0 | 0 | 0 | 20 | 2015-09-22 |  | 2016-01-21 | Bug | 1702 | Publish FTP rates sheet fails when file already exists
4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  | 2015-11-20 | 2016-01-21 | Bug |  | Riskey process log revert logs to read the same way as the k2 process style
6 | 0 | 0 | 6 | 2 | 0 | 2 | 0 | 0 | 0 | 8 | 2015-11-23 | 2015-11-23 | 2016-01-21 | Story | 1725 | Remove noise for blank file imports for riskey process log
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 |  | 2015-12-11 | 2016-01-21 | Story | 1739 | Read accrueal valuation from element in database
7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  | 2015-12-09 | 2016-01-21 | Story | 1738 | Add additional net test for templated rate report
3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 2015-12-18 | 2015-12-18 | 2016-01-21 | Story |  | CFC to recovery move to keyblade
8 | 21 | 2 | 31 | 31 | 16 | 47 | 0 | 0 | 0 | 78 | 2015-09-07 | 2015-09-08 | 2016-01-21 | Story | 1695 | Investigate TDS values for feds monthend pnl
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 2015-12-17 | 2015-12-17 | 2016-01-21 | Story | 1742 | Add gold and bullion counterparties to series list types table
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 |  |  | 2016-01-21 | Bug | 1749 | Fix ncd rate report blank line
2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 3 |  | 2015-12-08 | 2016-01-21 | Story | 1732 | Modify the FTP rates monthly column to use the accrual rate instead of funding curve
1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2015-10-04 | 2015-10-04 | Investigation |  | Investigate performance of MSQL 05 after 2014 install
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 |  |  | 2016-01-21 | Bug | 1737 | Daily deals duplicates in riskey
3 | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 2015-12-04 |  | 2016-01-21 | Story | 1714 | Store potential violations alerts in the database to keep track of potential breaches
14 | 0 | 0 | 14 | 16 | 4 | 20 | 0 | 0 | 0 | 34 |  | 2015-11-02 | 2016-01-21 | Story | 1720 | Intraday liquidity risk management report enhancements
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 3 |  |  | 2016-01-21 | Story | 1724 | Add business unit to daily deals extract for riskey
2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 1 | 4 | 2015-11-30 |  | 2016-01-21 | Story | 1731 | Siebel import error
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 |  | 2015-12-03 | 2015-12-08 | Story | 1726 | Add the bid/ask diff to the potential violations alert details
2 | 1 | 0 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 6 |  | 2015-12-01 | 2016-01-21 | Investigation |  | markitwire swaptions on keyblade
3 | 2 | 1 | 6 | 1 | 0 | 1 | 1 | 0 | 1 | 8 |  | 2015-09-22 | 2015-10-26 | Story | 1699 | Remove WF ETL from KB
8 | 1 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 |  | 2015-10-12 | 2015-10-26 | Operational Demand | 1712 | Create backup script to backup file by date
2 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2015-10-02 | 2015-10-02 | 2015-10-26 | Bug |  | Timeout errors on post dev communication listener
3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2015-10-06 | 2015-10-08 | 2015-10-26 | Story |  | Upgrade SQL on post dev
1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 2015-10-09 |  | 2015-10-26 | Story | 1707 | Remove 5 day time window for maturity date of ncd to eliminate false postive breaches
7 | 1 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |  |  | 2015-10-26 | Story |  | Linux box for wiki
4 | 2 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2015-09-22 |  | 2015-10-26 | Failure Demand |  | Investigate impact of calypso changes scheduled for 8 oct
3 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2015-09-11 | 2015-09-11 | 2015-09-15 | Story | 1697 | Pull oracle values (rada) for HQA from IBD for complete recon
1 | 2 | 0 | 3 | 5 | 0 | 5 | 0 | 0 | 0 | 8 | 2015-08-21 | 2015-08-22 | 2015-10-26 | Story | 1700 | Make currency pnl work for any department
2 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 2015-10-06 | 2015-10-06 | 2015-10-06 | Story | 1704 | Allow level ??? to be changed without code change
2 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2015-10-06 | 2015-10-06 | 2015-10-26 | Story | 1705 | Change africa cfc file format for nigreria to match the new file format
3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | 2015-10-01 | 2015-10-01 | Story | 1703 | Add ability to specify value date for currency pnl report
25 | 15 | 1 | 41 | 2 | 0 | 2 | 0 | 0 | 0 | 43 | 2015-08-19 | 2015-08-19 | 2015-10-26 | Story | 1680 | Email micro service
2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2015-10-02 | 2015-10-26 | Story | 1710 | Select instruments for velocity clf instead of the entire portfolio for intraday as per the sarb approval
4 | 1 | 0 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 6 | 2015-08-31 |  | 2015-10-05 | Bug | 1686 | Incentage profile combo report failure
8 | 7 | 0 | 15 | 1 | 0 | 1 | 0 | 0 | 0 | 16 | 2015-08-04 | 2015-08-05 | 2015-10-05 | Failure Demand |  | Investigate feds monthend pnl reconciliation
2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2015-09-15 | 2015-09-15 | 2015-09-16 | Bug | 1693 | SFTP command not working on some ftp servers due to path building not being platform independent
6 | 6 | 0 | 12 | 1 | 0 | 1 | 0 | 0 | 0 | 13 | 2015-09-03 | 2015-09-03 | 2015-10-05 | Story | 1691 | Pnl reporting for rxx dept
1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 2015-10-05 | Failure Demand |  | Riskey new desks not loading
1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2015-09-04 | 2015-09-04 | 2015-09-14 | Story | 1692 | Add for clf to report on intraday liquidity
40 | 6 | 2 | 48 | 5 | 2 | 7 | 0 | 0 | 0 | 55 | 2015-06-17 | 2015-06-17 | 2015-09-14 | Story | 1642 | Produce daily maximum usage for liquidity on intraday risk management report (zar)
1 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 2015-09-09 | 2015-09-10 | 2015-09-14 | Story | 1694 | Add additional info to the NCD potential breaches report for efficient monitoring
13 | 2 | 0 | 15 | 9 | 0 | 9 | 0 | 0 | 0 | 24 | 2015-06-01 | 2015-06-01 | 2015-07-28 | Story | 1636 | Greenmodel csv from automated ftp rates
8 | 0 | 0 | 8 | 3 | 0 | 3 | 1 | 0 | 1 | 12 | 2015-08-12 | 2015-08-19 | 2015-09-09 | Story | 1674 | Add India to subs FTP reports
4 | 0 | 0 | 4 | 3 | 0 | 3 | 0 | 0 | 0 | 7 | 2015-08-31 | 2015-08-31 | 2015-09-09 | Story | 1685 | Add and delete buttons on FTP subs screen
16 | 1 | 0 | 17 | 14 | 1 | 15 | 0 | 0 | 0 | 32 | 2015-06-10 | 2015-06-10 | 2015-07-28 | Story | 1647 | Prepare intraday liquidity report for graphs
7 | 0 | 0 | 7 | 8 | 0 | 8 | 0 | 0 | 0 | 15 | 2015-06-18 | 2015-06-18 | 2015-07-28 | Story | 1649 | Add the differences between new and previous ftp rates to automated ftp rates report
5 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2015-08-28 | 2015-08-28 | 2015-09-09 | Bug | 1684 | Rada BS recon discrepency
1 | 0 | 0 | 1 | 3 | 0 | 3 | 0 | 0 | 0 | 4 | 2015-08-31 | 2015-08-31 | 2015-09-09 | Story | 1687 | Update NCD Violation to 1000 million (upper limit)

## Simplified Average Allocation
Work type | Story
Average Days in Build | Average Days in Accept | Average Days in Over Production
6.541 | 3.0656 | 0.14754

## Complete Average Allocation
Work type | Story
Build (Busy) | Build (Not Busy) | Build (Waiting for Accept) | Accept (Busy) | Accept (Not Busy) | Over Prod (Busy) | Over Production (Not Busy)
4.9016 | 1.4426 | 0.19672 | 2.6066 | 0.45902 | 0.098361 | 0.04918

## Build Average Allocation
Work type | Story
Average of Bulid Busy | Average of Build Idle | Average of Build Wait for Accept
4.9016 | 1.4426 | 0.19672

## Accept Average Allocation
Work type | Story
Average of Accept Busy | Average of Accept Idle
2.6066 | 0.45902